## defect_pareto_log
Defect_ID | Date_Found | Lot | Defect_Type | Layer | Count | Severity | Root_Cause | Status
DEF-001 | 2026-01-11 | LOT-V7-001 | Slurry Residue Micro-Bridge | Metal 3 | 184 | Critical | Excessive CMP platen down-force (2.8 psi) causing Cu puddling | Closed
DEF-002 | 2026-01-11 | LOT-V7-001 | Edge Exclusion Bead Open | Metal 1 | 42 | Medium | Wafer edge photoresist bead removal overshoot | Closed
DEF-003 | 2026-01-12 | LOT-V7-001 | Inter-Level Dielectric Erosion | ILD-3 | 96 | High | Inadequate polish stop selectivity on Ta barrier | Closed
DEF-004 | 2026-01-15 | LOT-V7-002 | Particle Flake Bridging | Poly Gate | 14 | Low | Chamber liner flaking during LPCVD deposition | Closed
DEF-005 | 2026-01-19 | LOT-V7-002 | Dense Bus Signal Line Short | Metal 3 | 152 | Critical | CMP dishing across tight-pitch parallel logic buses | Closed
DEF-006 | 2026-01-25 | LOT-V7-003 | Contact Via Incomplete Etch | Via 2 | 28 | High | Polymer accumulation in reactive ion etch chamber | Closed
DEF-007 | 2026-02-01 | LOT-V7-004 | Residual Copper Micro-Smear | Metal 3 | 36 | Medium | Down-force reduced to 2.1 psi; minor lingering puddles | Closed
DEF-008 | 2026-02-05 | LOT-V7-004 | High-Voltage IO Leakage | IO Ring | 68 | High | Undersized 120um ESD rail-clamp NMOS baseline leakage | Superseded
DEF-009 | 2026-02-12 | LOT-V7-005 | Passivation Pinhole | Nitride | 11 | Low | Pre-cleansed scrub brush contamination | Closed
DEF-010 | 2026-02-19 | LOT-V7-006 | Slurry Scratch Void | Metal 2 | 8 | Medium | Abrasive agglomeration in polish slurry loop; filter replaced | Closed
DEF-011 | 2026-02-27 | LOT-V7-007 | Bond Pad TaN Barrier Peel | Top Metal | 6 | Medium | Over-exposure during pad etch photolithography | Closed
DEF-012 | 2026-03-09 | LOT-V7-005 | Gate Dielectric Rupture Short | Active/GOX | 3 | Critical | HTOL failure: 120um clamp thermal runaway & snapback failure | Superseded
DEF-013 | 2026-03-11 | LOT-V7-005 | Silicon Filament Melt | Contact/M1 | 3 | Critical | Secondary breakdown spiking during continuous 150C HTOL bias | Superseded
DEF-014 | 2026-03-18 | LOT-V7-009 | Outer Kerf Line Delamination | Kerf Dicing | 9 | Low | Dicing street test structure stress concentrator | Closed
DEF-015 | 2026-03-26 | LOT-V7-011 | Metal 1 Voiding | Metal 1 | 5 | Low | Electromigration barrier deposition shadow effect | Closed
DEF-016 | 2026-04-01 | LOT-V7-013 | Poly Resistance Offset | Poly Res | 12 | Medium | Furnace thermal gradient during annealing step | Closed
DEF-017 | 2026-04-19 | LOT-V7-020 | Random Airborne Particle | Metal 4 | 4 | Low | Rev B first lot: isolated cleanroom fallout (<0.02/cm2) | Closed
DEF-018 | 2026-04-20 | LOT-V7-020 | Passivation Edge Chipping | Polyimide | 3 | Low | Wafer blade dicing vibration on test lot | Closed
DEF-019 | 2026-04-25 | LOT-V7-021 | Solder Ball Void (Package) | Leadframe | 2 | Low | Reflow profile temperature ramp rate adjustment | Closed
DEF-020 | 2026-05-01 | LOT-V7-022 | Minor Silicide Agglomeration | Active Salicide | 5 | Low | Rapid thermal anneal soak time tuned | Closed
DEF-021 | 2026-05-07 | LOT-V7-023 | Micro-Corrosion on Test Pad | Aluminum Pad | 2 | Low | Deionized water rinse cycle time increased post-saw | Closed
DEF-022 | 2026-05-13 | LOT-V7-024 | Mold Flash on Wettable Flank | QFN Flank | 4 | Low | Package mold clamp pressure recalibrated | Closed