# FASTCHIP SEMICONDUCTOR — NEW PRODUCT INTRODUCTION (NPI) CHECKLIST

**Product Name:** Volta-7 Automotive Powertrain Controller

**Document ID:** NPI-CHK-V7-2024

**Revision:** 2.1 (Post-Rev B Sign-Off)

**Program Manager:** Derek Cole | **PE Manager:** Lisa Park | **Quality Manager:** Anna Becker

**Customer:** NovaDrive Motors | **Target SOP Date:** June 2024

---

## Phase Gate Status Summary

| Phase Gate | Gate Title | Baseline Target | Actual Completion | Gate Status | Sign-off Owner |

|---|---|---|---|---|---|

| Gate 1 | Design Handoff & Tape-out (Rev A) | 2023-11-15 | 2023-11-20 | COMPLETED | Sara Nolan |

| Gate 2 | First Silicon Arrival & Sort Readiness | 2024-01-12 | 2024-01-15 | COMPLETED (Yield Red) | James Ortiz |

| Gate 3 | ATE Test Program & Sample Delivery | 2024-02-28 | 2024-03-01 | COMPLETED | Emma White |

| Gate 4 | AEC-Q100 Qual Readiness & HTOL Start | 2024-02-15 | 2024-02-16 | FAILED (Rev A short) | Kevin Tran |

| Gate 4R | Rev B Mask Tape-out & Silicon Recovery | 2024-03-25 | 2024-04-21 | COMPLETED | Derek Cole |

| Gate 5 | Reliability Qualification Sign-Off (Rev B) | 2024-04-30 | 2024-04-28 | COMPLETED | Kevin Tran |

| Gate 6 | Customer Quality Audit & Production PSW | 2024-05-15 | 2024-05-13 | APPROVED | Anna Becker |

---

## Phase 1: Design Handoff & Mask Tape-out

- [x] **1.1 Schematic & Architecture Freeze:** Frozen on Rev A.3 register architecture. (Sara Nolan — 2023-11-10)

- [x] **1.2 DRC / LVS Clean Verification:** Rev A approved with commercial ESD cell waiver; corrected in Rev B to enforce 280 µm automotive clamp macro clean DRC. (Sara Nolan — 2024-03-23)

- [x] **1.3 Design for Testability (DFT) Review:** Stuck-at coverage verified at 99.4%, Transition Delay coverage at 96.8%. (Emma White — 2023-11-14)

- [x] **1.4 Design-to-PE Handoff Sign-off:** Completed per revised SOP-PE-042 checklist. (Lisa Park — 2024-03-24)

## Phase 2: First Silicon & Wafer Sort Readiness

- [x] **2.1 Sort Hardware Verification:** Dual-DUT probe cards mounted and planarized on Tester 04. (Emma White — 2024-01-12)

- [x] **2.2 Baseline Wafer Sort Yield:** Rev A baseline opened at 41.2% (unacceptable); CMP recipe optimization improved Rev A to 55.0%; Rev B achieved 78.4%. (James Ortiz — 2024-04-21)

- [x] **2.3 Defect Density Tracking:** Defect density monitored through Penang fab inline metrology; baseline dropped from 0.82 to 0.18 defects/cm². (James Ortiz — 2024-04-22)

- [x] **2.4 Wafer Map Server Automation:** Automatic Klarf transfer enabled between Penang fab and Austin yield server. (James Ortiz — 2024-01-14)

## Phase 3: ATE Test Program & Sample Delivery

- [x] **3.1 Test Program Release:** Rev 1.0 released for sample screening; Rev 1.2 released with optimized dual-ADC parallel execution. (Emma White — 2024-03-05)

- [x] **3.2 Test Time Optimization:** Initial test time 6.40s reduced to 3.82s, then optimized to 3.14s (Target: <3.20s). (Emma White — 2024-04-21)

- [x] **3.3 Tri-Temp Screening Qualification:** Guardbands verified across -40°C, +25°C, and +125°C. (Emma White — 2024-04-25)

- [x] **3.4 Customer Sample Delivery:** 50 ES1 units delivered to NovaDrive on March 1, 2024; 100 Rev B production-grade samples delivered on April 25, 2024. (Tom Harris — 2024-04-25)

## Phase 4: Reliability Qualification (AEC-Q100 Grade 1)

- [x] **4.1 Stress Hardware Qualification:** HTOL burn-in boards, thermal sockets, and power supplies verified in Lab C. (Kevin Tran — 2024-02-14)

- [x] **4.2 HTOL Stress Testing (1000 Hours, TJ = 150°C):** Rev A failed at 500 hours (3/231 fails); Rev B successfully passed 1000 hours with 0/231 fails. (Kevin Tran — 2024-04-28)

- [x] **4.3 Temperature Cycling (1000 Cycles, -55°C to +150°C):** Passed 0/231 fails across 3 distinct lots. (Kevin Tran — 2024-04-28)

- [x] **4.4 Highly Accelerated Stress Test (HAST, 96 Hours, 130°C / 85% RH):** Passed 0/231 fails with zero corrosion or leakage drift. (Kevin Tran — 2024-04-27)

- [x] **4.5 ESD Characterization:** Human Body Model (HBM) passed >2.5 kV; Charged Device Model (CDM) passed >750 V on Rev B. (Rosa Santos — 2024-04-26)

## Phase 5: Production Ramp & Sign-Off

- [x] **5.1 8D Customer Corrective Action Closure:** CAR-2024-ND01 approved and closed by NovaDrive Quality. (Anna Becker — 2024-04-30)

- [x] **5.2 On-Site Customer Quality Audit:** NovaDrive on-site audit completed on May 12, 2024: 0 Major NCs, 2 Minor Observations. (Anna Becker — 2024-05-13)

- [x] **5.3 Part Submission Warrant (PSW) & PPAP Level 3 Approval:** Formally signed by NovaDrive VP Marcus Vance. (Tom Harris — 2024-05-13)

- [x] **5.4 Mass Production Release Sign-Off:** Executive authorization granted for Penang fab ramp to 200,000 units/month. (Mike Chen — 2024-05-13)