## action_item_tracker
ID | Date_Raised | Meeting_Ref | Owner | Action | Priority | Status | Due_Date | Closed_Date
ACT-001 | 2024-01-08 | Meeting #1 | Derek Cole | Update master NPI checklist with Rev A.3 pin verification gate | High | Closed | 2024-01-10 | 2024-01-10
ACT-002 | 2024-01-08 | Meeting #1 | Sara Nolan | Deliver frozen Rev A.3 register map and test vectors to Emma White | High | Closed | 2024-01-11 | 2024-01-11
ACT-003 | 2024-01-15 | Meeting #2 | James Ortiz | Send wafer defect map and CMP signature analysis to Penang fab engineering | Critical | Closed | 2024-01-17 | 2024-01-16
ACT-004 | 2024-01-15 | Meeting #2 | Rosa Santos | Perform SEM/FIB deprocessing on Bin 4 logic fails from Wafer 03 | Critical | Closed | 2024-01-22 | 2024-01-21
ACT-005 | 2024-01-22 | Meeting #3 | Emma White | Complete ATPG scan vector debug and OTP burn routine on Advantest V93000 | High | Closed | 2024-01-26 | 2024-01-26
ACT-006 | 2024-01-22 | Meeting #3 | Derek Cole | Coordinate emergency design-to-test work session between Emma White and Sara Nolan | Medium | Closed | 2024-01-23 | 2024-01-23
ACT-007 | 2024-01-29 | Meeting #4 | Sara Nolan | Author formal Design-to-PE Handoff Checklist covering DFT registers and DRC waivers | High | Closed | 2024-02-02 | 2024-02-02
ACT-008 | 2024-01-29 | Meeting #4 | Anna Becker | Integrate handoff checklist into FastChip QMS quality documentation portal | Medium | Closed | 2024-02-05 | 2024-02-04
ACT-009 | 2024-02-05 | Meeting #5 | James Ortiz | Track split-lot split run on Lot LOT-V7-006 with modified CMP recipe in yield tracker | High | Closed | 2024-02-09 | 2024-02-09
ACT-010 | 2024-02-05 | Meeting #5 | Rosa Santos | Publish formal Failure Analysis Report on Metal 3 CMP bridge defects | High | Closed | 2024-02-12 | 2024-02-11
ACT-011 | 2024-02-12 | Meeting #6 | Kevin Tran | Load 231 units into HTOL stress chambers and verify bias supply voltages | Critical | Closed | 2024-02-16 | 2024-02-16
ACT-012 | 2024-02-12 | Meeting #6 | Anna Becker | Review and archive chamber calibration certificates and qual travelers in QMS | Medium | Closed | 2024-02-18 | 2024-02-17
ACT-013 | 2024-02-19 | Meeting #7 | Emma White | Execute ATE screening on 80 packaged units to select 50 golden samples | Critical | Closed | 2024-02-27 | 2024-02-26
ACT-014 | 2024-02-19 | Meeting #7 | Tom Harris | Draft customer sample release memo with operating waivers and deliver to NovaDrive | Critical | Closed | 2024-02-28 | 2024-02-28
ACT-015 | 2024-02-26 | Meeting #8 | Emma White | Parallelize dual ADC linearity routines to shave 350ms off ATE test time | High | Closed | 2024-03-05 | 2024-03-04
ACT-016 | 2024-02-26 | Meeting #8 | Derek Cole | Coordinate dispatch of 50 ES1 units via express courier to NovaDrive Motors | Critical | Closed | 2024-02-28 | 2024-02-28
ACT-017 | 2024-03-04 | Meeting #9 | Kevin Tran | Complete 500-hour HTOL pull and execute tri-temp ATE electrical screening | Critical | Closed | 2024-03-11 | 2024-03-11
ACT-018 | 2024-03-04 | Meeting #9 | Derek Cole | Prepare customer PPAP documentation schedule assuming successful 500h gate | Medium | Closed | 2024-03-08 | 2024-03-08
ACT-019 | 2024-03-11 | Meeting #10 | Rosa Santos | Perform decapsulation, EMMI hotspot detection, and FIB cross-section on failing units | Critical | Closed | 2024-03-13 | 2024-03-13
ACT-020 | 2024-03-11 | Meeting #10 | Kevin Tran | Quarantine remaining 228 HTOL units and preserve chamber bias and environmental logs | Critical | Closed | 2024-03-12 | 2024-03-12
ACT-021 | 2024-03-14 | Meeting #11 | Rosa Santos | Finalize and distribute formal Failure Analysis Report FA-2024-0314 | Critical | Closed | 2024-03-15 | 2024-03-14
ACT-022 | 2024-03-14 | Meeting #11 | Sara Nolan | Pull design schematic and layout database for IO clamp replacement with automotive-grade 280µm cell | Critical | Closed | 2024-03-16 | 2024-03-15
ACT-023 | 2024-03-18 | Meeting #12 | Anna Becker | Lead 8D Corrective Action Report generation and coordinate technical exhibits with Rosa Santos | Critical | Closed | 2024-04-05 | 2024-04-05
ACT-024 | 2024-03-18 | Meeting #12 | Tom Harris | Issue formal executive response letter to Marcus Vance at NovaDrive Motors | Critical | Closed | 2024-03-20 | 2024-03-19
ACT-025 | 2024-03-22 | Meeting #13 | Sara Nolan | Complete DRC/LVS physical verification and release Rev B mask stream tape-out | Critical | Closed | 2024-03-23 | 2024-03-23
ACT-026 | 2024-03-22 | Meeting #13 | James Ortiz | Coordinate hot-lot expedition protocol with Penang fab operations | Critical | Closed | 2024-03-25 | 2024-03-24
ACT-027 | 2024-03-29 | Meeting #14 | Derek Cole | Monitor daily Penang fab WIP velocity for Lot LOT-V7-020 and provide morning updates | High | Closed | 2024-04-03 | 2024-04-03
ACT-028 | 2024-03-29 | Meeting #14 | Anna Becker | Finalize 8D report draft with Rosa's FA imagery for executive review | High | Closed | 2024-04-05 | 2024-04-05
ACT-029 | 2024-04-07 | Meeting #15 | Tom Harris | Transmit signed 8D report to NovaDrive executive quality management | Critical | Closed | 2024-04-08 | 2024-04-07
ACT-030 | 2024-04-07 | Meeting #15 | Anna Becker | Log 8D submission into FastChip customer CAR tracking database | Medium | Closed | 2024-04-08 | 2024-04-08
ACT-031 | 2024-04-21 | Meeting #16 | James Ortiz | Update yield tracker with complete 25-wafer sort results for Lot LOT-V7-020 | High | Closed | 2024-04-23 | 2024-04-22
ACT-032 | 2024-04-21 | Meeting #16 | Emma White | Hand off 500 tested dies to fast-track packaging for reliability qual build | Critical | Closed | 2024-04-22 | 2024-04-22
ACT-033 | 2024-04-28 | Meeting #17 | Kevin Tran | Publish completed Reliability Qualification Summary Report and sign off certificate | Critical | Closed | 2024-04-30 | 2024-04-30
ACT-034 | 2024-04-28 | Meeting #17 | Anna Becker | Update 8D report with D6 closure data and submit validation package to NovaDrive | Critical | Closed | 2024-04-30 | 2024-04-30
ACT-035 | 2024-05-05 | Meeting #18 | Anna Becker | Conduct internal dry-run audit with all track owners and verify traveler archives | High | Closed | 2024-05-08 | 2024-05-08
ACT-036 | 2024-05-05 | Meeting #18 | Tom Harris | Finalize audit agenda and logistics with NovaDrive audit delegation | High | Closed | 2024-05-09 | 2024-05-09
ACT-037 | 2024-05-13 | Meeting #19 | Anna Becker | Submit formal corrective action response for the two minor audit observations to NovaDrive | High | Closed | 2024-05-20 | 2024-05-18
ACT-038 | 2024-05-13 | Meeting #19 | Derek Cole | Release production purchase order schedule to Penang fab for 200k unit monthly volume | Critical | Closed | 2024-05-16 | 2024-05-15
ACT-039 | 2024-05-20 | Meeting #20 | Lisa Park | Update PE Division SOP-PE-042 with enhanced design handoff and reliability qual protocols | High | Closed | 2024-05-27 | 2024-05-25
ACT-040 | 2024-05-20 | Meeting #20 | Sara Nolan | Implement automated automotive ESD DRC rule decks across CAD tool flows | High | Closed | 2024-05-30 | 2024-05-28