## Slide 1: PE Division Quarterly Review — Q1 2024
Author: Lisa Park, Product Engineering Manager
Audience: FastChip Executive Committee & Engineering Operations
Date: March 28, 2024

## Slide 2: Title & Executive Summary
Title: Product Engineering Division Q1 2024 Executive Review
Subtitle: Volta-7 Automotive Ramp, Technical Containment, and Rev B Roadmap
Presenter: Lisa Park, Product Engineering Manager
Key Takeaways:
  First silicon arrived Jan 2024; initial wafer sort yield of 41.2% recovered to 58.2% via Penang Fab CMP optimization.
  Rev A qualification suffered a critical setback with 3 HTOL failures at 500 hours due to undersized IO clamp design.
  Emergency Rev B redesign committed to mask shop on March 23; silicon arrival locked for April 21.
  Team alignment and engineering containment executing to maintain NovaDrive Motors June 2024 SOP.
Notes: Good morning leadership team. Q1 has been the most demanding quarter in PE history. While the HTOL failure tested our resilience, our rapid root-cause isolation and Rev B tape-out preserve our June customer commitments.

## Slide 3: PE Organization & Headcount
Division Overview: Total division headcount stands at exactly 20 dedicated engineers across two primary sites.
Austin HQ Team (14 Engineers):
  Product Engineering Leadership (Mike Chen, Lisa Park)
  Yield & Defect Analysis (James Ortiz)
  ATE Test Development & Tri-Temp Lab (Emma White + 3 test engineers)
  Reliability & Qualification Lab (Kevin Tran + 2 rel technicians)
  Quality Management & Customer Interface (Anna Becker, Tom Harris)
  Physical Failure Analysis Lab (Rosa Santos + 2 FA specialists)
  NPI Program Management & Design Interface (Derek Cole, Sara Nolan)
Penang Operations Team (6 Engineers):
  Fab Process Integration, Probe Sort Floor, and Backend Packaging Engineering.
Notes: Our lean 20-person engineering organization demonstrated world-class cross-functional agility, moving from failure detection to physical cross-section in 72 hours.

## Slide 4: Volta-7 Silicon Status & Ramp Timeline
Target Application: High-Voltage Inverter Controller for NovaDrive Motors 2025 EV Platform.
Process Technology: 130nm BCD Automotive Node (Penang Fab 2), 48-pin QFN package.
Ramp Milestones:
  Jan 08: Silicon ramp kickoff.
  Jan 15: First silicon sort (Lot 1): 41.2% yield (RED).
  Feb 05: CMP defect identified, yield reaches 54.8% (YELLOW).
  Mar 01: 50 ES1 engineering samples delivered to NovaDrive.
  Mar 11: HTOL 500h failure detected (CRITICAL RED).
  Mar 23: Rev B mask tape-out released.
  Apr 21 (Target): Rev B first silicon arrival at Austin sort.
  May 12 (Target): NovaDrive On-Site Supplier Audit.
  Jun 2024: Mass Production SOP.
Notes: The timeline is extremely tight with zero margin for error. Rev B silicon arrival on April 21 is the foundational milestone for customer audit approval.

## Slide 5: Q1 Yield Trajectory & Fab Improvement
Yield Trajectory:
  Jan baseline: 41.2% (Lot LOT-V7-001, heavy Bin 4 logic scan failures).
  Feb recovery: 54.8% (Lot LOT-V7-004, initial CMP down-force reduction).
  Mar baseline: 58.2% (Lot LOT-V7-013, stable CMP process window).
  Ramp Entitlement Model: 70.0% target; Rev B projection is 78%–82%.
Yield Loss Breakdown & Resolution:
  Bin 4 (Logic Scan BIST): Caused by Metal 3 copper CMP dishing. Resolved by lowering platen down-force (2.8 to 2.1 psi) and high-selectivity slurry.
  Bin 7 (Analog IDDQ Leakage): Attributable to Rev A IO clamp design weakness. Fixed in Rev B mask.
Notes: James Ortiz's data proves the fab process is fixed. The remaining yield gap on Rev A was purely design-limited by the IO clamp leakage, which Rev B eliminates.

## Slide 6: Reliability Qualification & HTOL Escalation
Qualification Standard: AEC-Q100 Grade 1 (-40°C to +125°C ambient, TJ = 150°C).
Rev A HTOL Performance:
  168-Hour Readout: 231/231 Passed (0 fails).
  500-Hour Readout: 3/231 Failed (catastrophic pin short to ground on Units U042, U089, U115).
Failure Analysis Findings (Rosa Santos):
  Hotspot localized via EMMI to primary ESD rail clamp.
  FIB confirmed gate oxide dielectric puncture and silicon melt filament.
  Physical cause: Commercial 120µm clamp macro used instead of 280µm automotive cell.
Reliability Next Steps: Full qualification retest on Rev B silicon utilizing accelerated 168h screen + 1000h qual chamber.
Notes: Kevin Tran and Rosa Santos isolated this to layout cell substitution. While painful, the root cause is completely deterministic and 100% resolvable in Rev B.

## Slide 7: ATE Test Program & Test Time Optimization
Test Platform: Advantest V93000 (Pin Scale 1600 / SmarTest 8).
Test Coverage Metrics:
  Digital Scan ATPG: 99.4% stuck-at coverage, 96.8% transition delay coverage.
  Analog / Mixed-Signal: Full CAN-FD loopback, high-voltage charge pump, and ADC linearity.
Test Time Optimization Progress:
  Initial Test Program: 6.40 seconds (unacceptable capacity bottleneck).
  Rev 1.0 Release: 3.82 seconds.
  Rev 1.2 Optimization: Shaving dual-ADC conversion from sequential to parallel execution.
  Target Budget: <3.20 seconds (Projected Rev B: 3.14 seconds).
Notes: Emma White's optimization work ensures our test time budget will be beaten, protecting gross margins during high-volume production.

## Slide 8: Critical Risks & Containment Plan
Risk 1: Rev B Fab Execution Slip
  Mitigation: Fab tagged 5 base lots at Poly gate; hot-lot metallization cycle time guaranteed at 20 days.
Risk 2: Customer Relationship with NovaDrive
  Mitigation: Full transparency; 8D report submitted April 7; daily technical touchpoints via Tom Harris.
Risk 3: Test Floor Capacity during Retest
  Mitigation: Pre-dedicated Tester 04 and two calibrated HTOL ovens in Lab C reserved exclusively for Rev B arrival.
Notes: Our mitigation matrix is fully active. Derek Cole tracks wafer WIP movement daily with Penang operations.

## Slide 9: Q2 2024 Objectives & Milestones
April 21: Receive Rev B silicon; achieve >75% wafer sort yield.
April 28: Complete accelerated reliability readout (HTOL/TC/HAST) with zero failures.
May 05: Complete internal dry-run for customer audit.
May 12: Successfully pass NovaDrive on-site supplier qualification audit.
May 20: Conduct PE division retrospective.
June 2024: Authorize commercial mass production release (200k units/month).
Notes: Bottom line: Q2 is about flawless execution. We have the technical solution, the team, and the customer alignment to cross the finish line.