## Slide 1: Volta-7 Ramp Status — March 2026
Author: Derek Cole, NPI Program Manager
Program: FastChip Volta-7 / NovaDrive Motors EV Inverter
Date: March 27, 2026

## Slide 2: Program Status & Executive Overview
Project: Volta-7 Automotive Grade 1 Power Management Controller
Customer: NovaDrive Motors Inc. (Platform: 2027 EV Drivetrain)
Program Manager: Derek Cole | PE Lead: Lisa Park
Overall Program Health: YELLOW (Recovery Mode)
  Silicon Design: Re-opened for Rev B Tape-out (Masks released Mar 21).
  Manufacturing: Penang Fab processing 5 hot-lots with modified CMP recipe.
  Customer Interface: Formal 8D containment active; customer committed to May audit.
Notes: This briefing summarizes our NPI recovery posture following the Rev A HTOL excursion. Our critical path is tightly coupled to the April 19 Rev B silicon dock date.

## Slide 3: NPI Program Dashboard
Milestone Tracking Table:
  Design Tape-out (Rev A): Completed Nov 17, 2025 [Status: Green]
  Wafer Sort Baseline: Completed Jan 12, 2026 — Yield 41.2% [Status: Red / Recovered to Yellow]
  Sample Delivery (50 ES1): Completed Feb 27, 2026 [Status: Green]
  HTOL Reliability Qual (Rev A): FAILED Mar 9, 2026 [Status: RED]
  Rev B Mask Tape-out: Completed Mar 21, 2026 [Status: Green]
  Rev B Silicon Arrival: Target Apr 19, 2026 [Status: Yellow / Tracking on-time]
  NovaDrive On-Site Audit: Target May 10, 2026 [Status: Yellow]
  Production Ramp (SOP): Target June 2026 [Status: Yellow]
Notes: HTOL is our single red gate. Every other deliverable has been held on schedule through intense team focus.

## Slide 4: Rev A HTOL Excursion & Root Cause Summary
Failure Description: 3 units failed at 500-hour HTOL readout (U162, U189, U215 from Lot LOT-V7-005).
Physical Analysis Summary (Rosa Santos):
  Short circuit on Pin 14 (CAN_TX) and high leakage on Pin 22 (LIN_IO).
  OBIRCH and EMMI pinpointed breakdown to primary ESD rail clamp.
  FIB revealed gate oxide blowout and silicon filamentation.
Root Cause Classification:
  Inadvertent substitution of 120µm commercial clamp macro in place of required 280µm automotive cell to resolve layout pitch congestion.
  Design verification rule gap allowed layout waiver without PE reliability approval.
Notes: The excursion was thoroughly investigated. Having absolute physical proof of the root cause prevented wasted fab cycles and allowed immediate silicon redesign.

## Slide 5: Rev B Recovery Schedule & Fab Milestones
Fast-Track Fabrication Strategy:
  Penang Fab 2 held 5 wafer lots at Poly Gate stage (pre-metallization base wafers).
  Rev B requires only 4 mask changes: Contact, Metal 1, Via 1, Metal 2.
Detailed Timeline to Silicon Dock:
  March 21: Mask database tape-out released to Penang mask shop.
  March 25: Reticles inspected, verified, and loaded onto lithography cluster.
  March 26 – April 16: Hot-lot metallization (LOT-V7-020 through LOT-V7-024).
  April 17: Wafer fab-out, passivation, and back-grind complete.
  April 18: Dedicated courier air shipment from Penang to Austin.
  April 19: Dock in Austin; immediate wafer sort on Tester 04.
Notes: By utilizing pre-built poly base wafers, we compressed a normal 12-week fab cycle into exactly 20 days.

## Slide 6: NovaDrive EV Ramp Commitments & Sample Delivery
Customer Deliverable Matrix:
  ES1 Samples (50 Units): Shipped Feb 27. Quarantined to room-temp lab evaluation.
  8D Report Submission: D1–D5 delivery committed for April 05.
  Rev B Fast-Track Samples: 100 fully screened QFN-48 units scheduled for delivery April 23.
  Production Part Approval Process (PPAP): Level 3 documentation submission scheduled for May 8.
  Supplier Quality Audit: Austin facility audit confirmed for May 10.
Customer Sentiment: Critical but supportive; NovaDrive has maintained their production allocation pending audit results.
Notes: Tom Harris has managed customer communications flawlessly. NovaDrive is holding their vehicle line for us, but May 10 is their non-negotiable deadline.

## Slide 7: Risk Mitigation Matrix & Path to Green
Remaining Project Risks:
  1. Probe Card Availability: Tester 04 probe card cleaned and re-aligned; spare card verified.
  2. Packaging Turnaround: Fast-track wire-bond line reserved in Penang assembly for 48-hour turn.
  3. Reliability Chamber Readiness: Kevin Tran has pre-wired Chambers 2 and 3 with calibrated sockets.
Exit Criteria for GREEN Program Health:
  Rev B sort yield >75%.
  Zero failures in Rev B early-life and HAST screening, with HTOL on track for 1000 hours.
  Closure of 8D report CAR-2026-ND01.
Notes: The entire team knows their role. If we execute to this plan, Volta-7 will be Green by late April.